## Sheet1
Backlog
describtion | status
login page | sprint 1
signup page | sprint 1
transaction menu | sprint 2
transfer money | sprint 2
manage account | sprint 2
fast cash | sprint 3
forget password ? | sprint 3
curency exchange | sprint 3
Creating GUI
confermition | sprint 3
sprint -1 | start | 2018-03-07
| finsh | 2018-03-21
Feature | Tascks | Roule | Duration | Status
login page | Login requirements gathering | Alaa,Haidi | 2h | completed
| Login page paper prototype | Alaa,Haidi | 1h | completed
| Login page design implement | Momen,Amr | 2h | completed
| creatiing login related columns in Database | Mahmoud | 1h | completed
| connecting database with login GUI | Momen,Amr | 2h | completed
| test login service | Alaa,Haidi | 30m | completed
SignUp page | SignUp page paper prototype | Alaa,Haidi | 2h | completed
| SignUp page design implement | Momen,Amr | 2h | completed
| connecting database with signUp GUI | Momen,Amr | 2h | on track
| creatiing login related columns in Database | Mahmoud | 1h | on track
| test signup service | Alaa,Haidi | 30m | on track
Setting Project Plange | Scenario | Team | 2h | completed
| User stories | Team | 2h | completed
| Project backlog | Team | 2h | completed
| Feature title description | Team | 2h | completed
| Functional & non-Functional requirments | Team | 2h | completed
| Documentation | Team | 2h | completed
| Schedule | Team | 2h | completed
sprint -2 | start | 2018-03-22
| finsh | 2018-04-06
Feature | Tascks | Roule | Duration | Status
transaction menu | the menu requirement gathering | alaa,haidi | 1h | not completed
| the menu page paper prototype | alaa,haidi | 1h | not completed
| the menu GUI | momen,amr | 2h | not completed
| the implemetion of GUI design | amr,mahmoud | 2h | not completed
| test the menu service | mahmoud | 30m | not completed
transfer money | transfer money requirement gathering | alaa,haidi | 2h | not completed
| transfer money page paper prototype | alaa,haidi | 1h | not completed
| transfer money design implemented | momen,amr | 3h | not completed
| create database | mahmoud | 1h | not completed
| connecting database with GUI | mahmoud | 2h | not completed
| test the transfer money service | alaa,haidi | 30m | not completed
manage account | manage account requirement gathering | alaa,haidi | 2h | not completed
| manage account page paper prototype | alaa,haidi | 2h | not completed
| manage account design implemented | amr,mahmoud | 3h | not completed
| create database | momen | 2h | not completed
| connecting database with GUI | alaa,haidi,amr | 3h | not completed
| test manage account service | momen,mahmoud | 1h | not completed
sprint -3 | start | 2018-04-07
| finsh | 2018-04-21
Feature | Tascks | Roule | Duration | Status
fast cash | the fast cash requirement gathering | alaa,haidi | 1h | not completed
| the fast cash page paper prototype | alaa,haidi | 2h | not completed
| the fast cash design implement | momen,amr | 3h | not completed
| create database | mahmoud | 2h | not completed
| connecting database with GUI | mahmoud | 3h | not completed
| testing fast cash service | alaa,haidi | 30m | not completed
forget password | forget password requirement gathering | alaa,haidi | 2h | not completed
| forget password page paper prototype | alaa,haidi | 1h | not completed
| forget password GUI design | mahmoud | 2h | not completed
| implement of GUI design | momen,amr | 3h | not completed
| testing forget password service | mahmoud | 30 m | not completed
confermation | confermation requirement gathering | alaa,haidi | 1h | not completed
| confermation page paper prototype | alaa,haidi | 1h | not completed
| confermation design implement | momen,amr | 2h | not completed
| connecting database with GUI | mahmoud | 3h | not completed
| test the confirmation service | alaa,haidi | 30m | not completed
curency exchange | curency exchange requirement | alaa,haidi | 2h | not completed
| curency exchange page paper prototype | alaa,haidi | 1h | not completed
| curency exchange design implement | momen,amr | 3h | not completed
| connecting database with GUI | mahmoud | 2h | not completed
| test curency exchange service | alaa,haidi | 30m | not completed