## Sheet1
Backlog
Describtion | Status
login page | sprint 1
signup page | sprint 1
transaction menu | sprint 2
Balance inquiry | sprint 2
transfer money | sprint 2
Show information | sprint 3
Log out | sprint 3
add new card | sprint 4
change passeword | sprint 4
change PIN | sprint 4
sprint -1 | start | 2018-03-07
| finsh | 2018-03-21
Feature | Tascks | Roule | Duration | Status
Setting Project Plange | Scenario | Team | 2h | completed
| User stories | Team | 2h | completed
| Project backlog | Team | 2h | completed
| Feature title description | Team | 2h | completed
| Functional & non-Functional requirments | Team | 2h | completed
| Documentation | Team | 2h | completed
| Schedule | Team | 2h | completed
login page | Login requirements gathering | Alaa,Haidi | 2h | completed
| Login page paper prototype | Alaa,Haidi | 1h | completed
| Login page design implement | Momen,Amr | 2h | completed
| creatiing login related columns in Database | Mahmoud | 1h | completed
| connecting database with login GUI | Momen,Amr | 2h | completed
| test login service | Alaa,Haidi | 30m | completed
SignUp page | SignUp page paper prototype | Alaa,Haidi | 2h | completed
| SignUp page design implement | Momen,Amr | 2h | completed
| connecting database with signUp GUI | Momen,Amr | 2h | completed
| creatiing login related columns in Database | Mahmoud | 1h | completed
| test signup service | Alaa,Haidi | 30m | completed
sprint 2 | start | 2018-03-22
| finsh | 2018-03-29
Feature | Tascks | Roule | Duration | Status
transaction menu(Home page) | transactions menu requirement gathering | Alaa,Haidi | 1h | completed
| transactions menu paper prototype | Alaa,Haidi | 1h | completed
| transactions menu GUI | Alaa,Haidi | 2h | completed
| test the menu service | Momen,Amr | 30m | completed
transfer money | transfer money requirement gathering | Momen,Mahmoud | 2h | completed
| transfer money paper prototype | Momen,Mahmoud | 1h | completed
| transfer money GUI implementing | Momen,Mahmoud | 3h | completed
| createing and connecting database columns relatred to transfer money | Momen,Mahmoud | 1h | completed
| test the transfer money service | Alaa,Haidi | 30m | completed
balance inquiery | manage account requirement gathering | Momen,Amr | 2h | completed
| manage account paper prototype | Amr | 1h | completed
| manage account GUI implementing | Amr | 3h | completed
| createing and connecting database columns related to manage account | Momen,Amr | 3h | completed
| test manage account service | Alaa,Haidi | 1h | completed
sprint 3 | start | 2018-03-30
| finsh | 2018-04-19
Feature | Tascks | Roule | Duration | Status
Show information | Show information requirement gathering | alaa,haidi | 2h | completed
| Show information page paper prototype | alaa,haidi | 1h | completed
| createing and connecting database columns related to Show information | Momen | 3h | completed
| test Show information service | mahmoud,Amr | 30 m | completed
Log out | Log out requirement gathering | alaa,haidi | 5m | completed
| Log out implement | momen,amr | 5m | completed
| test Log out | alaa,haidi | 1 m | completed
sprint 4 | start | 2018-04-19
| finsh | 2018-04-26